## Daily Task Tracker
🚀 AIOps Internship — Daily Task Tracker
Project: AIOps ¦ Start Date: 26 March 2026 ¦ Tools: Kubernetes · Helm · OpenShift · ML · Data Preprocessing
# | Start Date | End Date | Day | Task / Activity | Tool / Technology | Status | Product / Module | Notes
1 | 26-Mar-2026 | 26-Mar-2026 | Thursday | Orientation & environment setup | Kubernetes / Minikube | ✅ Completed | AIOps - Infra
2 | 27-Mar-2026 | 27-Mar-2026 | Friday | Study Kubernetes core concepts (pods, services) | Kubernetes | ✅ Completed | AIOps - Infra
3 | 30-Mar-2026 | 30-Mar-2026 | Monday | Deploy sample app on Minikube | Kubernetes / Helm | ✅ Completed | AIOps - Infra
4 | 31-Mar-2026 | 31-Mar-2026 | Tuesday | Learn Helm chart structure & templating | Helm | ✅ Completed | AIOps - Infra
5 | 01-Apr-2026 | 01-Apr-2026 | Wednesday | Deploy n8n workflow automation on K8s | Kubernetes | ✅ Completed | AIOps - Automation
6 | 02-Apr-2026 | 02-Apr-2026 | Thursday | OpenShift introduction & comparison with K8s | OpenShift | ✅ Completed | AIOps - Infra
7 | 03-Apr-2026 | 03-Apr-2026 | Friday | Data collection & exploration for AIOps dataset | Python / Pandas | ✅ Completed | AIOps - ML
8 | 06-Apr-2026 | 07-Apr-2026 | Monday | Data preprocessing: cleaning & normalization | Python / Scikit-learn | ✅ Completed | AIOps - ML
9 | 08-Apr-2026 | 09-Apr-2026 | Wednesday | Feature engineering for anomaly detection | Python / ML | 🔄 In Progress | AIOps - ML
10 | 10-Apr-2026 | 13-Apr-2026 | Friday | Build & train anomaly detection model | ML / Scikit-learn | ⏳ Pending | AIOps - ML
11 | 14-Apr-2026 | 16-Apr-2026 | Tuesday | Containerize ML model with Docker | Docker / Kubernetes | ⏳ Pending | AIOps - Infra
12 | 17-Apr-2026 | 20-Apr-2026 | Friday | Deploy ML model on OpenShift cluster | OpenShift / Helm | ⏳ Pending | AIOps - Deployment
13 | 21-Apr-2026 | 24-Apr-2026 | Tuesday | Set up monitoring with Prometheus & Grafana | Kubernetes / Helm | ⏳ Pending | AIOps - Monitoring
14 | 27-Apr-2026 | 30-Apr-2026 | Monday | Integrate model with n8n automation pipeline | n8n / Kubernetes | ⏳ Pending | AIOps - Automation
15 | 01-May-2026 | 05-May-2026 | Friday | Testing, documentation & final presentation | All Tools | ⏳ Pending | AIOps - Final

## Summary
📊 Internship Progress Summary
Intern Name
Internship Start | 26-Mar-2026
Expected End
Organization
Supervisor
Project | AIOps
Status | Count
✅ Completed | 8
🔄 In Progress | 1
⏳ Pending | 6
❌ Blocked | 0
Total Tasks | 15
Legend / Status Guide
✅ Completed | Task fully done
🔄 In Progress | Currently working on it
⏳ Pending | Not started yet
❌ Blocked | Waiting on dependency